## Risk Register
Victorial Health Risk Register
Risk id | Description | Category | Likekihood | Impact | Inherent Risk Score | Existing controls | Residual Risk Score | Risk Owner | Treatment Plan | Status
R-001: Unpatched Medical IoT Devices | There is a risk that threat actors could exploits unpathced madical IoT devices on patient network due to outdated firmware leading to unauthorised PHI access, patient safety incidents and regulatory penalties under HIPAA | Cyber | 4 - Likely. 47 devices, no patches 18 months, manufacturer unresponsiv | 4 - Major. PHI breach + patient safety + fine 500K-5M | 16 Critical | Basic firewall, but no VLAN segmentation for IoT | 15 - High. Firewall not designed for IoT lateral movement | Hospital IT Managers – Mysuru, Kolar, Mangalore | Mitigate - 1. Network segmentation for IoT 2. Vendor escalation for patches 3. Compensating control: IDS monitoring | Open
R-002: Inconsistent Password Policies | There is a risk that inconsistent password policies across acquired hospitals due to lack of centralized IAM standards could lead to credential compromise, unauthorized PHI access, and HIPAA violations. | Compliance | 4 – Likely. 3 of 4 hospitals have weak/no MFA. Prior auth attacks observed | 4 – Major. PHI breach affects 50K+ patients. Fine 500K-5M + patient trust loss. | 16 Critical | Mysuru: 12-char + MFA. Kolar: 8-char no MFA. Mangalore: No documented policy. | 15 - High. Existing controls only cover 25% of users. | Hospital IT Managers – Mysuru, Kolar, Mangalore | Mitigate – 1. Board-approved Password Standard 2. Enforce MFA on all privileged + remote access 30 days 3. Audit AD monthly | Open
R-003: No Incident Response Plan | There is a risk that the absence of a tested incident response plan across Victoria Health due to post-acquisition gaps could lead to delayed containment of cyber events, resulting in extended outages, regulatory fines for late breach notification, and patient safety impact. | Operational | 4 – Likely. Kolar ransomware scare took 72hrs. No tabletop done. 3 hospitals = 3x attack surface. | 5 – Catastrophic. HIPAA breach notification >60 days = fines. Downtime stops surgeries = patient safety ZERO appetite breach. | 20 Critical | Ad-hoc: IT Manager phone tree, firewall logs exist but no SIEM, no on-call rotation | 15 - Critical. Ad-hoc response provides no measurable reduction. | Hospital IT Managers – Mysuru, Kolar, Mangalore | Mitigate – 1. Publish IR Plan + RACI in 30 days 2. Run tabletop with IT + Legal + CMO Q2 3. Implement 24/7 SOC monitoring | Open

## Risk_Appetite_Statement
Risk Category | Appetite Level | Source Threshold | Rationale
Patient Safety | Zero | 1 unacceptable | Board mandate
Compliance | Low | 4 unacceptable | HIPAA fine
Operational | Moderate | 9 unacceptable | Sometimes down OK
Financial | Moderate | 9 unacceptable | <500K without board
Reputational | Low | 4 unacceptable | Trust critical

## Control_Inventory
Control ID | Control Name | Control Type | Nature | Status | Maps to risk id
C-001 | Network Firewall | Preventive | Technical | Partial | R-001
C-002 | MFA for priviledge | Preventive | Technical | Gap | R-002
C-003 | Password Policy | Preventive | Admin | Inconsistent | R-003
C-004 | IR Plan | Corrective | Admin | Gap | R-004
C-005 | Physical Locks | Preventive | Physical | Gap | R-005
C-006 | Security Awerness Training | Preventive | Admin | Gap | R-006
C-007 | SIEM Log Monitoring | Detective | Technical | Partial | R-007
C-008 | Vendor Due Delligence Process | Preventive | Admin | Gap | R-008
C-009 | Backup & Restore Tests | Corrective | Technical | Inconsistent | R-009
C-010 | CCTV for Filing Rooms | Detection | Physical | Gap | R-010

## Vendor_Risk_Assessment
Vendor Name | Data Shared | Inheretent Risk | Due Deligence Done | Residual Risk | Decision
MedicareBillingCo | PHI, Billing, SSN | 16 – Critical. No SOC2 report provided | Requested ISO 27001 cert. Got nothing | 16 - Critical | Remediate: Contract pause in 30d if no cert